## Sheet1
id | epic | tasks | status | estimation | actual effort | started date | finished date
1 | delivrable | Write features list | doing | 2h | 1.5h | Mar, 2023 | Not finished
2 | delivrable | Wirte versions plan | done | 1/2h | 1h | Mar, 2023 | 2023-03-30
3 | delivrable | Write user manual | done | 2h | 1/2h | Mar, 2023 | 2023-03-27
4 | delivrable | Write technical design document | to do | 2.5h |  | Feb,2023 | Not finished
5 | delivrable | Wirte test plan | to do | 2h |  | Mar,2023 | Not finished
6 | delivrable |  | to do
7 | test | Test UI loading properly | doing | 1/2h | 10min | Mar,2023 | Not finished
8 | test | Test scene image loading | done | 1/2h | 15min | Jan,2023 | 2023-04-29
9 | test | Test Scenario Switching | to do | 1/2h | 1/2h | Feb, 2023 | Not finished
10 | test | Test character model loading | doing | 1/2h | 1h | Mar, 2023 | Not finished
11 | test | Test character, scene, and prop interactions. | to do | 1h |  | Mar, 2023
12 | test | Test trigger conditions such as scene switching and story progression | doing | 1h |  | Apr.2023
13 | test |  | to do
14 | deployment | Development engine download and deployment | to do | 1/2h | 1h | Nov, 2022 | 2022-11-11
15 | deployment | Create project environment | to do | 2h |  | Nov, 2022 | 2022-11-20
16 | deployment | Game artist deployment | to do | 1h |  | Jan,2023
17 | deployment |  | to do
18 | design | Design UI | doing | 8h | 2h | Jan,2023 | Not finished
19 |  | Main menu UI（to be optimized） | doing | 2h | 2h | Jan,2023 | 2023-01-10
20 | design | Design the script (story) infrastructure | to do | 5days | 7days | Jan,2023 | 2023-02-10
21 | design | Script background introduction
22 | design | Character image design | to do | 2days |  | Jan,2023
23 | design | Design script important event | to do | 6h |  | Jan,2023
24 | design
25 | design | Designing Game Text | doing | 3days | 5days | Jan,2023 | Not finished
26 | design |  | to do
27 | implementation | Do RPGmaker MV tutorial | to do | 10days |  | Dec, 2022 | Jan,2023
28 | implementation | Do Unity tutorial | doing | 3days |  | Mar, 2023 | Apr.2023
29 | implementation | toturial about basic opterations | done | 2days | 1days | Jan,2023 | 2023-01-12
30 | implementation | toturial about events | done | 1days | 1days | Jan,2023 | 2023-01-14
31 | implementation | toturial about plugin
32 | implementation | Search and collect news events, social hot material and other references. | doing | during all project |  | Nov, 2022
33 | implementation | Art drawing | to do | during all project |  | Jan,2023
34
35 | features | features version1 | done | 1day | 1day | Apr.2023 | 2023-03-30
|  | Design Basic map (Trial version) | done | 1h | 3h | Mar,2023 | 2023-03-31
|  | Player (test) img loading. | done | 1h | 1h | Mar,2023 | 2023-03-31
|  | Player Movement (basic). | done | 2h | 2h | Apr,2023 | 2023-04-02
|  | Test | done | 1h | 1/2h | Apr,2023 | 2023-04-03
36 | features | features version2 | done | 3days | 3days | Apr.2023 | 2023-04-01
|  | Character movement animation. | done | 3h | 2h | Apr,2023 | 2023-04-03
|  | Character static/moving state switching. | done | 1/2h | 1/2h | Apr,2023 | 2023-04-03
|  | Virtual camera (follow player) | done | 1/2h | 1h | Apr,2023 | 2023-04-04
|  | main menu UI (loading) | done | 1/2h | 1/2h | Apr,2023 | 2023-04-04
|  | main menu UI (Function realization) | doing | 1h | 1.5h | Apr,2023 | 2023/4/5 (not finished)
|  | The main menu enters the game transition screen | done | 1/2h | 1/2h | Apr,2023 | 2023-04-04
|  | Test | done | 1h | 1h | Apr,2023 | 2023-04-05
37 | features | features version3 | doing | 3days |  | Apr.2023
38 | features | features version4 | to do | 5days |  | Apr.2023
39 | features | features version5 | to do | 5days |  | Apr.2023
40 | features | features version6 | to do | 5days |  | Apr.2023