## CLASS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6
Likelihood |  |  |  | Incredible | Improbable | Remote | Occasional | Probable | Frequent | Classification
Category | Rating | 1 | Negligible | 1 | 2 | 3 | 4 | 5 | 6 | N/ACC
frequent | 6 | 2 | Marginal | 2 | 4 | 6 | 8 | 10 | 12 | RFI
probable | 5 | 3 | Critical | 3 | 6 | 9 | 12 | 15 | 18 | ACC
occasional | 4 | 4 | Catastrophic | 4 | 8 | 12 | 16 | 20 | 24
remote | 3
improbable | 2
incredible | 1
Severity
Category | Rating
catastrophic | 4
critical | 3
marginal | 2
negligible | 1
Risk = Severity x Likelihood
Risk | Category
0… 6 | Acceptable (ACC)
7… 12 | Requires Further Investigation (RFI)
13… 24 | Not acceptable (N/ACC)

## RISK
Risk ID | Potential Risk | Cause ID | Potential Causes | Severity | Likelihood | Risk | Mitigation ID | Mitigation
R1.1 | Missed deadline | C1.1.1 | Illness | 1 | 3 | 3 | M1.1.1 | Register exceptional circumstances if ill.
|  | C1.1.2 | Cannot choose topic | 1 | 1 | 1 | M1.1.2 | Conduct research early and meet supervisor
|  | C1.1.3 | Poor time management | 4 | 3 | 12 | M1.1.3 | Make a Gantt plan early
R1.2 | Feature creep | C.1.2.1 | Over-ambitious project spec. | 3 | 2 | 6 | M1.2.1 | Discuss plan with supervisor early. Create basic (must-have) goals and enhancements (nice-to-have).
R1.3 | Software bugs | C1.3.1 | Non-modular design | 1 | 3 | 3 | M1.3.1 | Create highly modular desigh before implementation
|  | C1.3.2 | Poor test plan | 4 | 3 | 12 | M1.3.2 | Create test plan at start
R1.4 | Loss of data | C1.4.1 | Poor version control | 4 | 4 | 16 | M1.4.1 | Implement version control strategy at start.